## Gantt Schedule
WBS ID | Phase / Task | Owner | Start Week | End Week | Duration (Weeks) | Predecessor | Milestone
1.0 | Project Initiation | PM | 1 | 1 | 1 |  | Charter Approved
2.0 | Requirements | PM / Security Lead | 1 | 2 | 2 | 1.0 | Requirements Approved
3.0 | Solution Planning | Security Lead | 2 | 3 | 2 | 2.0 | Solution Plan Approved
4.0 | Implementation | Security Engineering | 3 | 6 | 4 | 3.0 | Core Implementation Complete
5.0 | Validation / UAT | Security Lead / SOC | 6 | 9 | 4 | 4.0 | UAT Complete
6.0 | Training & Enablement | PM / Security Lead | 9 | 10 | 2 | 5.0 | Training Complete
7.0 | Operational Handover | PM / IT Ops | 10 | 11 | 2 | 6.0 | Handover Complete
8.0 | Closure | PM / Sponsor | 11 | 12 | 2 | 7.0 | Project Closed