## RACI Matrix
Activity | Sponsor | Project Manager | Security Lead | SOC | IT Operations | Compliance
Project Charter | A | R | C | I | I | C
Requirements | I | A/R | R | C | C | C
Architecture | I | C | A/R | C | R | I
Log Onboarding | I | C | A | R | R | I
Detection Testing | I | C | A | R | C | I
UAT | A | R | R | R | C | C
Risk Management | A | R | C | C | C | C
Change Control | A | R | C | C | C | C
Training | I | A/R | R | C | C | I
Closure | A | R | C | C | C | C