## Risk Register
Risk ID | Risk | Category | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Owner | Status
R-01 | Log-source access delayed | Dependency | 4 | 5 | 20 | Critical | Mitigate — escalate access request | IT Ops | Monitoring
R-02 | Detection requirements change | Scope | 3 | 4 | 12 | High | Control — baseline/change process | Security Lead | Open
R-03 | Key resource unavailable | Resource | 3 | 4 | 12 | High | Mitigate — backup resource | PM | Monitoring
R-04 | Integration defects | Technical | 3 | 5 | 15 | Critical | Mitigate — early testing | Security Lead | Open
R-05 | UAT delays | Schedule | 2 | 4 | 8 | Moderate | Mitigate — reserve UAT capacity | PM | Monitoring
R-06 | Scope expansion | Scope | 4 | 4 | 16 | Critical | Avoid/Control — change management | Sponsor | Open
R-07 | Documentation incomplete | Quality | 2 | 3 | 6 | Moderate | Mitigate — documentation checklist | PM | Monitoring
R-08 | Training attendance low | Adoption | 2 | 3 | 6 | Moderate | Mitigate — scheduled sessions | PM | Monitoring