## RAID Log
ID | Type | Description | Owner | Due Week | Status | Action / Decision
RAID-01 | Risk | Priority log access delay | IT Ops | 4 | Open | Escalate access request
RAID-02 | Assumption | Required technical resources available | PM | 3 | Validated | Confirm weekly
RAID-03 | Issue | One integration produced incomplete events | Security Lead | 6 | Resolved | Reconfigure connector
RAID-04 | Dependency | Cloud team access required | Cloud Lead | 4 | Open | Track dependency
RAID-05 | Decision | Dashboard KPI set approved | Sponsor | 5 | Closed | Add to baseline
RAID-06 | Risk | Scope expansion request | Sponsor | 7 | Controlled | Use change process